Appendix D:   SOHPR Site Visit Preparation Tasks Checklist

How to use this checklist:

- Complete the third column by inserting specific due dates based on the scheduled date of your State Oral Health Program Review (SOHPR) site visit.

- When a task is completed, place a check mark in the last column.

| Activity/Event/Task | Timeline | Due Date | Completed |
| --- | --- | --- | --- |
| Receive call from ASTDD team leader to discuss potential dates of visit, logistics and team members. | Four months prior to the visit |  |  |
| Start preparing SOHPR briefing book | Three to four months prior to the visit |  |  |
| Complete SOHPR briefing book and send it to the team members and ASTDD National Office | Six weeks prior to the visit |  |  |
| Send draft agenda for the site visit and list of potential interviewees to the SOHPR team leader | Six weeks prior to the visit |  |  |
| Conference call with the SOHPR team leader to review and revise the agenda, list of interviewees and hotel arrangements. | Five weeks prior to the visit |  |  |
| Invite State Health Officer and others to participate in SOHPR site visit interviews and report read-out as appropriate. | Four weeks prior to the visit |  |  |
| If state is able to contribute to the cost of the visit: Negotiate cost-sharing arrangements with ASTDD SOHPR coordinator. | Four weeks prior to the visit |  |  |
| Conference call with SOHPR team to discuss briefing book and self-study, finalize agenda and logistics | Three weeks prior to the visit |  |  |
| Send interviewees agenda, information on the team and instructions | Three weeks prior to the visit |  |  |
| Arrange for conference rooms and necessary equipment and supplies for the team and the interviews | As soon as possible before the visit |  |  |